## Safeguarding Adults Action Plan
| Recommendation | Outcome | Action | Responsibility | Review date | Rag | Comments
1 | Raise awareness of Think Family philosophy | All relevant staff will have an understanding of the Think Family Strategy Guidance and processes; being able to quickly identify relevant cases and taking appropriate action | 1.1 Increase reference to think family within safeguarding adults training | 1.1 NSC | 1.1 Sept 18 | Blue
|  |  | 1.2 Learning event being held will include a link to think family | 1.2 DA Coordinator NSC | 1.2 March 2019 | Green | Will be delivered during 19/20 year
|  |  | 1.3 Partner agencys to review how Think Family is promoted within their organisations and report to Board on findings | 1.3 Multi-Agency/SAB | 1.3 Dec 18 | Green | Part of Quality & Perfromance sub-group work plan
|  |  | 1.4 Think family information embedded in landing page for safeguarding board website | 1.4 NSC | 1.4 Dec 18 | Blue
|  |  | 1.5 Appointment of dedicated prinipal social worker for adults | 1.5 QA Sub-Group | 1.5 August 18 | Blue
|  |  | 1.6 QA Group Audit to Focus on think family | 1.6 QA Sub-Group | 1.6 March 19 | Green
2 | The support for couples involved in situational violence can be improved | Support services will be available for adults in domestic abuse situations where the victim and perpertrator role can be described as interchangeable | Review of contractual expectations upon Domestic Abuse support provider | Domestic Abuse Coordinator (NSC) | 2019-03-01 | Green | The next domestic abuse support provider contract will start 1/4/20. The specification for this is being drafted (deadline for final draft May 2019). Partners are being consulted. A funding bid has been submitted to the MHCLG for training on reducing parental conflict for practitioners.
3 | Improvement can be made in the consistency of use of DASH risk assessments | Board will have received assurance that partners ensure staff receive consistent quality of training in DASH risk assessment which promotes the use of professional judgement | Through Board, partner agencies that use DASH will be identified and those organisations asked to report to Board what training staff have in the completion of DASH assessments | Multi-agency/SAB | 2019-03-01 | Green | DASH is embedded in domestic abuse multi-agency training, new 2 hour multi-agency sessions specifically upon DASH are being introduced, A session for MARAC representatives is being held on 11/3/19. Agency training on DASH and use of DASH will be ascertained as part of a wider review of responses to high risk domestic abuse. The report on this will be finalised by Dec 2019.
4 | Review North Somerset Safeguarding Adults Board Information Sharing Protocol and ensure that it encourages appropriate information sharing | Board will be assured that staff across partner agencies are able to appropriately share information | Publication of an updated information sharing protocol | NSSAB Policy & Procedures Sub-Group | 2018-09-01 | Blue
5 | Positive Steps: Review referral process and consider promoting the concept of appropriate information sharing and professional referrals. | Significant background information will be shared by professionals in order to inform eligibility decisions | Professional referral portal is available at positivestep.org.uk Positive step to work with Communication & Publicity sub-group to ensure this availability of this referral route is know to appropriate professionals | Positive Steps/Comms Sub-Group | 2018-09-01 | Blue
6 | Foster Carers are in a good position to challenge professional decision making | Foster carers are supported and empowered to raise concerns or disagreements with agencies | Empower foster carers to challenge decisions | Children Support and Safeguarding (NSC) | 2018-12-01 | Blue
7 | There is an opportunity to improve early access to psychological support for cheildren afected by parental suicide | 7.1 Winston's Wish training and promotional materials will have been shared with relevant partner agencies. | 7.1 Distribution of promotional materials for Winston's Wish provided to partner agencies | 7.1 Comms Sub Group | 2018-12-01 | Blue
|  | 7.2 Health services will be in a position to offer appropriate signposting at an early stage | 7.2 Relevant Health providers to review their procedures | 7.2 WAHT | 2018-12-01 | Blue
8 | A lack of clarity around charging for Relate services may lead to a retiscence to approach the service | Public will be clear in the circumstances under which relationship counselling charges can be waived. | Letter from Board Chair to suggest more detail around charging exemptions | NSSAB Chair | 2018-09-01 | Blue
9 | There is an opportunity to Improve safeguarding for young adults | Those working with vulnerable young people aged 17-25 will understand their role within safeguarding procedures | Position statement to be developed and shared across adults and children's services | P&P Sub-Group | 2018-06-01 | Blue
10 | Awareness of when to raise a safeguarding adults concern can be improved | Information and advice wil be readily available to asist people to make a decision as to when to rasie a safeguarding adults concern | Safeguarding adults flow chart will be publicly available promoting when to raise a concern and how | P&P Sub-Group & Comms Sub-Group | 2018-12-01 | Green | Ongoing programme of policy developments
|  |  | Key: | Blue |  | Complete
| VERSION CONTROL: V4 25.01.2019 |  |  | Red |  | No discernable progress
|  |  |  | Amber |  | Progress but timescales slipping
|  |  |  | Green |  | On track
Lessons Learned Review - Ms X
Action Plan

## Colour key
Rag
Blue
Green
Amber
Blue
Blue
Red
Amber
Amber
Amber
Blue
Blue
Red
Blue
Amber
Blue
Amber